## Functional
Project Name: | Self Embedding Watermarking System
Superviser Name: | Dr. Asif Mahmood Gilani
Deliverable: | Project Status
ID | Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | The system shall allow the user to place a watermark in an image | High | 100% | N/A | Arbab Hamd Rizwan, Usama Aslam
2 | The system shall allow the user to place a watermark in an video | High | 40% | Week 7 | Hunzlah Malik, Aashar Naseem
3 | The system shall allow the user to download watermarked images | Medium | 50% | Week 8 | Hunzlah Malik, Aashar Naseem
4 | The system shall allow the user to download watermarked videos. | Medium | 50% | Week 8 | Hunzlah Malik, Aashar Naseem
5 | The system shall allow the user to detect any tampering in watermarked images. | High | 100% | N/A | Arbab Hamd Rizwan, Usama Aslam
6 | The system shall allow the user to detect any tampering in watermarked videos. | High | 0% | Week 9 | Arbab Hamd Rizwan, Usama Aslam
7 | The system shall allow the user to view detection results on tampered images. | High | 100% | N/A | Hunzlah Malik, Aashar Naseem
8 | The system shall allow the user to view detection results on tampered videos. | High | 0% | Week 9 | Arbab Hamd Rizwan, Usama Aslam
9 | The system shall allow the user to reconstruct tampered images that have been watermarked by the system | High | 50% | Week 10 | Arbab Hamd Rizwan, Usama Aslam
10 | The system shall allow the user to reconstruct tampered videos that have been watermarked by the system | High | 15% | Week 12 | Arbab Hamd Rizwan, Usama Aslam
11 | The system shall allow the user to download reconstructed images. | High | 50% | Week 12 | Hunzlah Malik, Aashar Naseem
12 | The system shall allow the user to download reconstructed videos. | High | 50% | Week 8 | Arbab Hamd Rizwan, Usama Aslam
13 | The system shall generate reports on tampered regions of watermarked images. | Low | 20% | Week 8 | Arbab Hamd Rizwan, Usama Aslam
14 | The system shall generate reports on tampered regions of watermarked videos. | Low | 0% | Week 12 | Hunzlah Malik, Aashar Naseem
15 | The system shall allow the user to upload images and videos. | medium | 100% | N/A | Hunzlah Malik, Aashar Naseem

## Non-Functional
Project Name: | Self Embedding Watermarking System
Superviser Name: | Dr. Asif Mahmood Gilani
Deliverable: | Project Status
ID | Non-Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | Reusability - The system shall have a 100% uptime guarantee. | High | 50% | Week 8 | Hunzlah Malik, Aashar Naseem
2 | Performance - The system shall limit the size of the uploaded images or videos to 50MB | Medium | 100% | N/A | Hunzlah Malik, Aashar Naseem
3 | Performance - The system webpage shall load in 2 seconds. | Low | 20% | Week 9 | Hunzlah Malik, Aashar Naseem
4 | The system shall take an approximate time of less than 180 seconds (3 minutes) to embed watermark in an image | High | 100% | N/A | Arbab Hamd Rizwan, Usama Aslam
5 | Security - The system shall use a permutation key to place watermarks on images | High | 100% | N/A | Arbab Hamd Rizwan, Usama Aslam
6 | Extensibility - The system shall be generic i.e., it shall work with most image or video formats. | High | 80% | Week 11 | Hunzlah Malik, Aashar Naseem
7 | Usability - The system shall provide an easy to learn and navigate user interface | Medium | 100% | N/A | Arbab Hamd Rizwan, Usama Aslam

## Instructions
Instructions For Completing This Document
Complete the Project Name and Superviser Name
ID: A unique ID number used to identify the requirement
Functional Requirement: This column should be populated with a description of the functional requirement. | Non-Functional Requirement: This column should be populated with a description of the non-functional requirement.
Status: This column should be populated with the current status of the functional requirement.
Deadline: This column should be populated for the requirements whose status is incomplete.
Resource: Team member who completed/will complete the requirement implmentation.